## Sheet1
EMACS PROJECT SOFTWARE REQUIREMENTS SPECIFICATION / PROJECT OWNER: CREATIVE ENGINEERING SOLUTIONS LLC / MANAGER: jrom876 / CTO: jrom876 / ENGINEERING TEAM: Namick Elylrac (CH), Christopher David Leland Wells (CW), David Suave (DS), Romansapien (emeritus), jrom876 (JMR)

SOFTWARE REQUIREMENTS TRACEABILITY MATRIX
PROJECT MANAGER:	Jacob M. Romero			PROJECT ID:	EMACS-003
PROJECT OWNER:	Creative Engineering Solutions, LLC			PROJECT TITLE:	EMACS – Environmental Monitor and Control System
REQUIREMENT INFORMATION					RELATIONSHIP TRACEABILITY
ID	CATEGORY	REQUIREMENT	PRIORITY	ASSIGNEE	PERFORMANCE OBJECTIVE	DELIVERABLE(S)	VERIFICATION	VALIDATION
SW-REQ-001	SW Functional / Environmental Sensor Node	Weather Node SW Driver – senses CO2, temperature and humidity / Microcontrollers: Arduino Nano or Uno / Software: emacs_TX_dev.ino / Hardware: K30, DHT-11, NRF24	High	JMR	Collect CO2 and Temp/Humid status. / Publish Sensor Data to mosquitto server. / Receive frequency control and other commands from Node Controller.	emacs_TX_dev.ino	in progress	Pending
SW-REQ-002	SW Functional / Security Sensor Node	Physical Security Node SW Driver – senses intruders or breach of premises / Microcontrollers:Arduino Nano or Uno / Software: emacs_PS_dev.ino / Hardware: PIR, Audio Detector, Radar Module, NRF24	Low	JMR	Collect PIR, Camera, Radar, an/or Audio Detectors Data / Publish Sensor Data to mosquitto server. / Receive frequency control and other commands from Node Controller.	emacs_PS_dev.ino	in progress	Pending
SW-REQ-003	SW Functional / Environmental Sensor Node	Carbon Monoxide Sensor Node SW Driver / Microcontroller: Arduino Nano or Uno / Software: emacs_CO_dev.ino / Hardware: CO Sensor, NRF24	Medium	JMR	Collect CO Sensor Data / Publish Sensor Data to mosquitto server. / Receive frequency control and other commands from Node Controller.	emacs_CO_dev.ino	in progress	Pending
SW-REQ-004	SW Functional / Node Controller	Node Controller SW Driver / Microcontroller: Arduino Mega 2560 / Software: emacs_RX_dev.ino or ADF4351_LCD-main / Hardware: NRF24, LCD 4x16 or ADF4351	High	JMR	Monitor and Control Sensor Nodes / Control Safety Devices: Visual and Audio Space Warnings; Ventilation; CO2 Sources	emacs_RX_dev.ino / or / ADF4351_LCD_EMACS.ino	in progress	Pending
SW-REQ-005	SW Functional / Sensor		Medium	Namick_Elylrac			needs definition of flash profiles	Pending
SW-REQ-006	SW Functional / pH Controller	PH Sensor Node / Microcontroller: Arduino Nano or Uno / Software: emacs_pH_dev.ino / Hardware: PH Sensor, NRF24	High	CW	Collect pH Sensor Data / Publish Sensor Data to mosquitto server. / Receive frequency control and other commands from Node Controller.	emacs_pH_dev.ino	Architecture Completed / Needs integration and debug	Pending
SW-REQ-007	SW Functional / PPM Controller	PPM Sensor Node / Microcontroller: Arduino Nano or Uno / Software: emacs_PPM_dev.ino / Hardware: PPM Sensor, NRF24	High	CW	Collect PPM Concentration Sensor Data / Publish Sensor Data to mosquitto server. / Receive frequency control and other commands from Node Controller.	emacs_PPM_dev.ino	not started	Pending
SW-REQ-008	SW Functional / Environmental Sensor Node	Combustible Gas Sensor Node / Arduino Nano or Uno / Software: emacs_CG_dev.ino / Gas Sensor, NRF24	Medium	JMR	Collect Combustible Gas Sensor Data / Publish Sensor Data to mosquitto server. / Receive frequency control and other commands from Node Controller.	emacs_CG_dev.ino	not started	Pending
SW-REQ-009	SW Functional / CO2 Tank Controller	CO2 Tank Actuator Node / Arduino Nano or Uno / Software: emacs_CO2_tank_control_dev.ino / Analog or discrete actuator, NRF24	Medium	JMR	Control Tank Actuator / Publish actuator status to mosquitto server / Receive frequency control and other commands from Node Controller.	emacs_CO2_tank_control_dev.ino	not started	Pending
SW-REQ-010	SW Functional / Fan Controller	Fan Controller Node / Arduino Nano or Uno / Software: emacs_fan_control_dev.ino / Analog or discrete fan, NRF24	Medium	JMR	Control Fan Actuator / Publish actuator status to mosquitto server / Receive frequency control and other commands from Node Controller.	emacs_fan_control_dev.ino	not started	Pending
SW-REQ-011	SW Functional / Light Controller	Light Controller Node / Arduino Nano or Uno / Software: emacs_light_control_dev.ino / Analog or discrete light controller, NRF24	Medium		Control Light Actuator / Publish actuator status to mosquitto server / Receive frequency control and other commands from Node Controller.	emacs_light_control_dev.ino	not started
SW-REQ-012	SW Functional / Sensor	reserved	Medium	JMR	Arduino Arducam OV7670 / 34685-MP Doppler Radar Motion Sensor / 32361-MP Smoke and Combustible Sensor		Architecture Completed / Needs integration and debug	Pending
SW-REQ-013	Enclosure	Aesthetic enclosure design required.	High	DS	Enclosure design with UI/UX considerations for maximum aesthetic and functional value.	enclosure.dwg	not started	Pending
SW-REQ-014	Enclosure	IP51 enclosure rating: limited dust ingress with protection against condensation	Medium	DS	Gives lowest acceptable level of device environmental protection required for production and sales.	enclosure.dwg	not started	Unit test and UAT.
SW-REQ-015	Enclosure	IP-64 enclosure with forced air flow for k30 and DHT-11 sensors	Low	DS	Gives highest level of device environmental protection required for this application.	enclosure.dwg	not started	Pending
SW-REQ-016	SW Functional / LP_Jetson		Medium	JMR			Architecture Completed / Needs integration and debug	Pending
SW-REQ-017	HW Safety	Battery Backup required for DFD regulations if unit is controlling CO2 dispenser	High	CSO	Battery Backup must switch on when power is lost within xx milliseconds while maintaining system control.		Needs definition	Pending
SW-REQ-018	HW Safety	Incorporated CO (Carbon Monoxide) Sensor	High	CSO	Provides indication of CO danger due to incomplete combustion if natural gas CO2 generators are used.		Future Expansion	Pending
SW-REQ-021	SW Functional / LP_Jetson	Python Test GUI	Medium	JMR	Develop GUI for testing and implementing laser driver on bench		in progress	Pending
SW-REQ-022	SW Functional	Hello World, wakeup and initialization in situ	Medium	Unassigned	Out of box wake up and initialization routine	name of software deliverable or algorithm goes here	queued
SW-REQ-023	SW Functional	asset tracking w tamper detection and gps	Medium	Unassigned	Inventure Track device, or some other asset tracking device	name of software deliverable or algorithm goes here	queued
SW-REQ-024	SW Functional	code obfuscation	Medium	Unassigned	After software validation, we will discuss the need for code obfuscation	name of software deliverable or algorithm goes here	queued
SW-REQ-025	SW Functional	ssd data storage	Medium	Unassigned	on-board removable data storage device	name of software deliverable or algorithm goes here	queued
SW-REQ-026	SW Functional	phone app	Medium	Unassigned	gives user real-time video and security updates	name of software deliverable or algorithm goes here	queued
SW-REQ-027	SW Functional	bluetooth interface	Medium	Unassigned	"move back", or other audible commands or warning sounds	name of software deliverable or algorithm goes here	queued
SW-REQ-028	SW Functional	wi fi interface	Medium	Unassigned		name of software deliverable or algorithm goes here	queued
SW-REQ-029	SW Functional		Medium	Unassigned			queued
SW-REQ-030	SW Functional	graphics generator	Medium	Unassigned
SW-REQ-031	SW Functional	mounting orientation	Medium	Unassigned
SW-REQ-032	SW Functional	siren interface	Medium	JMR
SW-REQ-033	SW Functional		Medium
SW-REQ-034	Nice to have		Low
SW-REQ-035	Mandatory		High
SW-REQ-036	Should have		Medium
SW-REQ-037	Nice to have		Low
SW-REQ-038	Mandatory		High
SW-REQ-039	Should have		Medium
SW-REQ-040	Nice to have		Low